## Slide 1
JIRA ESSENTIALS
From Backlog to Done — Navigating JIRA for Agile Teams
45-Minute Session | Follow-on from SDLC & Agile Fundamentals

## Slide 2
Session Agenda
45 minutes • Recap → Tool Walkthrough → Hands-on Concepts → Q&A
Quick Recap
SDLC & Agile — how JIRA fits in
5 min
JIRA Core Concepts
Projects, Issues, Workflows, Boards
10 min
UI Walkthrough
Backlog, Board, Issue Detail View
15 min
Sprints in Action
Planning, tracking, closing a sprint
8 min
Reports & JQL
Burndown, velocity, quick search
5 min
Wrap-up & Q&A
Key takeaways + open floor
2 min
JIRA Essentials | 2

## Slide 3
Quick Recap: Where JIRA Fits
You've learned SDLC phases and Agile/Scrum principles. JIRA is the tool that operationalizes them.
Plan
Backlog grooming, epics & stories
→
Build
Sprint board, task tracking
→
Track
Status transitions, comments
→
Release
Version/fix tagging, reports
Key Idea
JIRA doesn't replace Agile ceremonies — it gives them structure. Every sprint planning meeting, standup, and retro references data living inside JIRA: the backlog, the board, and the issue history.
JIRA Essentials | 3

## Slide 4
Core Concept: Issue Hierarchy
Everything in JIRA is an 'Issue' — but issues nest into a hierarchy.
EPIC
Large body of work, spans multiple sprints
STORY / TASK
User-facing requirement or work item
SUB-TASK
Smaller technical steps within a story
BUG
Defect logged against any level above
Tip: In Oracle Fusion / ADF-style delivery work, teams often map Epics to a release theme, and Stories to individual integration or pipeline builds.
JIRA Essentials | 4

## Slide 5
JIRA UI: The Backlog
Where product owners groom and prioritize upcoming work before a sprint starts
Projects / Data-Platform-Migration / Backlog
SPRINT 14 (12 Jul – 25 Jul) • 34 story points
Start Sprint
DPM-142
Build ADF pipeline for HR staging load
5
DPM-143
Fix ORCID sequence collision (PER-1532552)
3
DPM-144
Add async token refresh to Fusion connector
8
DPM-145
Design Synapse serverless pool for reporting
13
Backlog list
Unstarted issues ranked by priority, top = next to pick up
Sprint grouping
Issues are dragged into a Sprint container before it starts
Story point estimate
Relative effort sizing used for velocity & capacity planning
Issue type icon
Story, Task, Bug, Epic — colour-coded for quick scanning
JIRA Essentials | 5

## Slide 6
JIRA UI: The Sprint Board
The live workspace the team uses daily to track progress during a sprint
Board / Sprint 14 / Active Sprint
TO DO
DPM-146
PGP encryption setup for SFTP feed
DPM-147
Add retry logic to token fetch
IN PROGRESS
DPM-143
Fix ORCID sequence collision
DPM-144
Async concurrency w/ semaphore
DPM-148
Unity Catalog RDD restriction fix
IN REVIEW
DPM-140
Metadata-driven pipeline template
DONE
DPM-138
OAuth bearer token helper function
DPM-139
Derived column decimal pattern fix
JIRA Essentials | 6

## Slide 7
JIRA UI: Issue Detail View
Click any card to open full detail — description, status, comments, and history
DPM-143 Fix ORCID sequence collision (PER-1532552)
IN PROGRESS
Description
Dynamic sequence numbers collide when concurrent PATCH requests hit the ORCID_Inbound staging table. Add jittered backoff + per-row sequence locking in the Azure Function processor.
Activity
RK: Added Retry adapter w/ urllib3 — testing token refresh path.
RK: Reproduced PER-1532552 on staging; root cause = race condition.
System: Status changed To Do → In Progress
Details
Assignee
Ram K.
Reporter
Priya S.
Priority
High
Sprint
Sprint 14
Story Points
3
Labels
oracle-fusion, hcm
Fix Version
v2.4.1
JIRA Essentials | 7

## Slide 8
Sprint Lifecycle in JIRA
A repeating loop — this is what the team does every 2 weeks
1. Plan Sprint
Drag prioritized backlog items into the sprint
→
2. Start Sprint
Set duration + goal, board activates
→
3. Daily Standup
Move cards across columns as work progresses
→
4. Review & Close
Complete/carry-over issues, sprint report generated
Loop continues → Sprint 15 planning begins right after closing Sprint 14
JIRA Essentials | 8

## Slide 9
Reports & Quick Search (JQL)
Reports
Burndown Chart
Remaining work vs. time left in sprint
Velocity Chart
Story points completed sprint over sprint
Cumulative Flow
Work distribution across statuses over time
JQL — JIRA Query Language
project = DPM AND status = "In Progress" AND assignee = currentUser() AND labels = "oracle-fusion"
Use JQL to build custom filters and save them as dashboard widgets or personal shortcuts.
Try it live:
Search bar (top of JIRA) → type g then g → Quick navigate. Or open Filters → Advanced Issue Search to write JQL directly.
JIRA Essentials | 9

## Slide 10
Key Takeaways
JIRA turns Agile ceremonies into trackable, auditable workflow data
Backlog → Sprint Board → Done is the core operational loop
Issues follow a hierarchy: Epic → Story/Task → Sub-task, with Bugs anywhere
Every issue carries full context: assignee, status, comments, history
JQL and Reports turn raw issue data into team & stakeholder insight
Next Session Idea: Hands-on lab — create a project, log issues, and run a mock sprint
JIRA Essentials | 10

## Slide 11
Questions?
Thank you! Let's discuss anything you'd like to explore further in JIRA.